# How to Implement the AI Council in 30 Days

This page outlines how organizations typically move from receiving the AI Council Starter Kit to running a functioning, decision-making AI Council within the first month.

This is not a transformation plan. It is an execution sequence.

## Week 1: Establish Authority and Scope

Primary goal: Make the AI Council real, not symbolic.

What happens:

- Executive sponsor is named and confirms decision authority

- Council membership is finalized (no observers by default)

- Initial scope is defined:

  - What types of AI decisions belong here

  - What decisions explicitly do not

Common failure to avoid:
 Launching the Council without executive authority, turning meetings into status updates instead of decisions.

## Week 2: Run the First Council Meeting

Primary goal: Prove the cadence works.

What happens:

- First meeting is held using the provided agenda

- At least one real decision is made and logged

- Initial tool inventory or use-case list is reviewed

- Owners and review dates are assigned

Success signal:
 The Decision Log has entries after the first meeting.

## Week 3: Introduce Measurement (Lightweight)

Primary goal: Shift from discussion to outcomes.

What happens:

- 1–2 workflows are selected for ROI tracking

- Baselines are agreed upon (conservative, not perfect)

- Monthly ROI scorecard is populated with initial data

- Reporting format is aligned with leadership expectations

Common failure to avoid:
 Waiting for “perfect data” before measuring anything.

## Week 4: Stabilize the Operating Rhythm

Primary goal: Make the Council self-sustaining.

What happens:

- Second and third meetings reinforce cadence

- Escalation path is tested at least once

- Security and compliance reviews are flowing through the Council, not around it

- Leadership receives the first summarized update

Success signal:
 AI decisions are no longer happening ad hoc outside the Council.

## What Typically Breaks Without Ongoing Ownership

Organizations often implement the structure successfully, but then struggle with:

- Maintaining prioritization as AI requests increase

- Keeping ROI measurement consistent

- Balancing speed with security as usage scales

- Preventing decision drift back to informal channels

This is usually where teams either:

- Assign clear, ongoing internal ownership, or

- Bring in a fractional Chief AI Officer to run the cadence, coordination, and reporting.

## When a Conversation Is Useful

A short conversation is usually helpful if:

- You want to sanity-check Council membership or authority

- You are unsure how much ownership IT vs business should have

- You want help setting conservative, defensible ROI baselines

- You want to pressure-test whether this should be internally owned or externally supported

There’s no obligation to proceed further. The goal is clarity.

### Optional Closing CTA (keep understated)

If it would be helpful to talk through how this would apply in your context, I’m happy to do that.

## Final recommendation

If you choose just one and standardize it everywhere:

### Primary Button

Pressure-Test This in Your Context

### Optional subtext under the button (small, grey)

No obligation. Used to clarify ownership, cadence, and next steps.

That pairing maximizes trust and reply-to-call rates.